SmartBracket™

March Madness 2026

Strategic Execution Plan

Dan Lipsy

President & COO

Supported Intelligence LLC

January 2026

SI Strategic Document 2026-2

# Executive Summary

Based on comprehensive analysis of SmartBracket's codebase, 9-year performance history, and market dynamics, this plan recommends a fundamental repositioning for 2026:

Stop treating SmartBracket as a revenue business. Start treating it as your most compelling sales asset.

SmartBracket's 9-year track record of ~90th percentile performance is worth more as a credibility engine for Supported Intelligence's enterprise RRToolbox offerings than as a $2,107/5-year consumer product.

## Strategic Priorities

| Priority | Objective | Investment |
| --- | --- | --- |
| 1 | MDP vs. LLM Bake-Off 2.0 (Credibility Campaign) | $2,000-5,000 |
| 2 | Supported Intelligence Website Integration | $0 (student labor) |
| 3 | Controlled Marketing Experiment | $1,000-2,000 |
| 4 | Enterprise Lead Generation | $0-1,000 |

Total Recommended 2026 Budget: $3,000-8,000 (vs. $9,461 spent on failed paid media 2022-2024)

# 1. Strategic Repositioning

## 1.1 The Problem with Current Approach

| Metric | Historical (2020-2024) | Implication |
| --- | --- | --- |
| Total Revenue | $2,107 | Product not viable at scale |
| Total Marketing Spend | $16,897 | 8x revenue spent on acquisition |
| Customer Acquisition Cost | $37.98-$94.08 | Losing $33-89 per customer |
| Consumer Market Trend | Commoditizing (free AI) | Getting worse, not better |

Continuing the current approach will lose more money.

## 1.2 The New Positioning

| Old Positioning | New Positioning |
| --- | --- |
| SmartBracket is a consumer product | SmartBracket is a demonstration |
| Goal: Acquire paying users | Goal: Generate enterprise leads |
| Success metric: Revenue | Success metric: Qualified leads for RRToolbox |
| Marketing: Paid acquisition | Marketing: Content + credibility |

## 1.3 Why This Works

The 9-year track record cannot be bought – It's your most defensible asset

Free AI makes consumer market unprofitable – But increases interest in "beating AI"

Enterprise customers want proof – SmartBracket IS the proof

March Madness gets attention – Use that attention for Supported Intelligence

# 2. MDP vs. LLM Bake-Off Campaign 2026

## 2.1 Campaign Concept

"MDP vs. LLM Showdown 2026"

Build on the 2025 bake-off with an expanded, more visible competition that positions Supported Intelligence as the authority on optimization vs. AI.

## 2.2 Bracket Categories

| Category | Method | Purpose |
| --- | --- | --- |
| SmartBracket MDP | Pure RRToolbox optimization | Showcase core technology |
| SmartBracket + User Input | MDP with 3-question adjustments | Show personalization value |
| Claude/GPT/Gemini | Top 3 LLMs, identical prompt | Benchmark against AI hype |
| Hybrid: LLM → MDP | LLM picks fed into MDP as locked picks | Novel approach, good story |
| Hybrid: MDP → LLM | MDP recommendations given to LLM | Alternative hybrid |
| ESPN Smart Bracket | ESPN's tool | Free baseline comparison |
| Chalk Bracket | All favorites | Naive baseline |
| Random Student Picks | GVSU/Turkey student brackets | Human baseline |

## 2.3 Campaign Timeline

### Pre-Tournament (February 15 - Selection Sunday)

| Week | Activity | Owner | Cost |
| --- | --- | --- | --- |
| Week 1 | Publish "2025 Bake-Off Results" blog post | Student Team | $0 |
| Week 1 | Create 2026 methodology page | Student Team | $0 |
| Week 2 | Set up tracking infrastructure | Student Team | $0 |
| Week 2 | Recruit LLMs for competition | Student Team | $0 |
| Week 3 | Generate all brackets | Student Team | $0 |
| Selection Sunday | Publish all brackets publicly | Student Team | $0 |

### Tournament Phase (March)

| Activity | Frequency | Owner | Cost |
| --- | --- | --- | --- |
| Daily leaderboard updates | Daily | Student Team | $0 |
| Weekly analysis posts | Weekly | Student Team | $0 |
| Social media updates | Daily during games | Student Team | $0 |
| Final results & analysis | Post-tournament | COO + Student Team | $0 |

# 3. Student Resource Plan

## 3.1 Available Resources

Two student resource pools are available for 2026 execution:

| Resource | Location | Strengths | Considerations |
| --- | --- | --- | --- |
| Grand Valley State University | Michigan, USA | Local, same timezone, campus resources | Higher hourly rate ($15-20/hr) |
| International Students | Turkey | Lower cost, strong technical skills | Timezone difference (8 hrs), remote only |

## 3.2 Recommended Team Structure

| Role | Source | Hours/Week | Duration | Est. Cost |
| --- | --- | --- | --- | --- |
| Content Lead | GVSU | 8-10 | Feb-Apr (12 wks) | $1,440-2,400 |
| Social Media Coordinator | Turkey | 5-8 | Feb-Apr (12 wks) | $300-600 |
| Data Analyst | Turkey or GVSU | 5-8 | Mar-Apr (6 wks) | $300-960 |

Total Student Labor Budget: $2,040-3,960

## 3.3 Task Allocation

### GVSU Student (Content Lead)

Write all blog posts and long-form content

Create methodology documentation

Coordinate with COO on messaging

Quality control on all public materials

Lead LinkedIn content strategy

Handle any in-person campus promotion

### Turkey Student(s) (Execution Support)

Daily social media posting (Twitter/X during games)

Create graphics and infographics

Update tracking spreadsheets

Monitor and respond to social engagement

Research competitor brackets

Compile data for analysis

# 4. Budget Summary

## 4.1 2026 Investment Allocation

| Category | Low Estimate | High Estimate |
| --- | --- | --- |
| GVSU Student Labor | $1,440 | $2,400 |
| Turkey Student Labor | $600 | $1,560 |
| LinkedIn Promoted Posts | $300 | $500 |
| Content/Design Tools | $200 | $500 |
| Miscellaneous | $200 | $400 |
| TOTAL | $2,740 | $5,360 |

## 4.2 Comparison to Historical Spend

| Year | Spend | Result |
| --- | --- | --- |
| 2022 | $5,750 | 49 users, $117 CAC |
| 2023-24 | $9,461+ | Negative ROI |
| 2026 (recommended) | $2,740-5,360 | Enterprise leads + credibility |

## 4.3 ROI Scenario Analysis

| Scenario | Probability | Enterprise Value | ROI |
| --- | --- | --- | --- |
| 1 enterprise deal closes | 30% | $50,000-500,000 | 10x-100x |
| 2-3 qualified leads | 50% | $10,000-50,000 pipeline | 2x-10x |
| Credibility only | 90% | Hard to quantify | Positive |
| Complete failure | 10% | $0 | -100% |

Expected Value: Even with 30% probability of closing one enterprise deal ($50K-500K), the expected value far exceeds the investment.

# 5. Execution Timeline

## 5.1 January 2026 (Preparation)

| Week | Milestone | Deliverable | Owner |
| --- | --- | --- | --- |
| Jan 20-26 | Security fixes | MD5 replaced, secrets removed | Dev |
| Jan 20-26 | Student recruitment | Offers extended | COO |
| Jan 27-Feb 2 | Student onboarding | Access granted, training | COO |
| Jan 27-Feb 2 | Tool setup | Social accounts, analytics | Student Team |

## 5.2 February 2026 (Pre-Tournament)

| Week | Milestone | Deliverable | Owner |
| --- | --- | --- | --- |
| Feb 3-9 | 2025 results published | Blog post live | Content Lead |
| Feb 10-16 | 2026 methodology finalized | Methodology page live | COO + Content |
| Feb 17-23 | Bracket generation | All brackets ready | Student Team |
| Feb 24-Mar 2 | Selection Sunday prep | All content staged | Student Team |

## 5.3 March 2026 (Tournament Execution)

| Week | Milestone | Deliverable | Owner |
| --- | --- | --- | --- |
| Selection Sunday | Brackets published | All brackets public | Student Team |
| Round 1-2 | Daily tracking begins | Daily leaderboard updates | Turkey Student |
| Sweet 16 | Mid-tournament analysis | Analysis blog post | Content Lead |
| Final Four/Champ | Peak engagement | Real-time updates | Full Team |

## 5.4 April 2026 (Post-Tournament)

| Week | Milestone | Deliverable | Owner |
| --- | --- | --- | --- |
| Apr 7-13 | Final results analysis | Comprehensive results report | COO + Content |
| Apr 14-20 | Case study creation | SI website updated | Content Lead |
| Apr 21-30 | Lead follow-up | Outreach to inquiries | COO |

# 6. Success Metrics

## 6.1 Primary KPIs (Enterprise Focus)

| Metric | Target | Measurement |
| --- | --- | --- |
| Enterprise inquiries from bake-off | 5-10 | Contact form submissions |
| Qualified enterprise opportunities | 2-3 | Passed qualification questions |
| SI website traffic increase | +50% during Mar-Apr | Google Analytics |
| LinkedIn engagement | 1,000+ impressions | LinkedIn analytics |

## 6.2 Secondary KPIs (Demonstration Success)

| Metric | Target | Measurement |
| --- | --- | --- |
| SmartBracket vs. LLM performance | Top 3 in bake-off | Tournament results |
| Bake-off content views | 500+ | Blog analytics |
| Email list growth | +100 subscribers | MailChimp |
| Media mentions | 1-2 | Google Alerts |

# 7. Risk Assessment

## 7.1 Risks & Mitigations

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| SmartBracket underperforms | 30% | High | Frame as "one year" vs. 9-year track record |
| No enterprise leads generated | 40% | Medium | Content still has SEO/credibility value |
| Student unavailability | 20% | Medium | Have backup students identified |
| Security breach (MD5) | 10% | Critical | Fix before tournament (P0 priority) |
| LLMs significantly improve | 50% | Medium | Emphasize consistency, not single-year |

## 7.2 Contingency Plans

If SmartBracket underperforms:

Emphasize 9-year track record vs. single year

Highlight variance in LLM performance

Focus on "consistency" narrative

If no enterprise leads:

Content still builds SEO and credibility

Learnings inform 2027 approach

Consider academic publication route

# 8. Immediate Actions

The following actions should be taken immediately to execute this plan:

| Priority | Action | Timeline | Owner |
| --- | --- | --- | --- |
| P0 | Fix MD5 security vulnerability | This week | Dev |
| P0 | Remove hardcoded FB secret | This week | Dev |
| P1 | Recruit GVSU student (Content Lead) | Jan 20-27 | COO |
| P1 | Identify Turkey student(s) | Jan 20-27 | COO |
| P2 | Update SI website with SmartBracket integration | Feb 1-15 | Student Team |

— End of Strategic Plan —

Prepared by Claude Code Business Analysis Framework

For Supported Intelligence LLC | January 2026